# Monthly Project Report

# Team Members:

Liam, Bryce, Mitchell, Adam

# Dated

28.10.25

## Procurement progress and tracking

All procurement was finalised in September; no new items were required this month. Only reinstallation of software which incurred no cost.

Existing hardware and virtual machines continued to be used with no replacements, failures, or additional costs.

## Project progress to timelines

October was heavily focused on troubleshooting and correcting firewall and routing issues, which caused minor delays but resulted in major progress in network stability.

Significant time was spent resolving:

Firewall outbound access issues

NAT configuration problems

DNS resolution and access between internal networks and the DMZ

Windows Server issues accessing the DMZ website were resolved by updating the hosts file, allowing successful communication.

The DMZ PC previously receiving an incorrect 169.x.x.x APIPA address was fixed by adjusting switch configurations and ensuring proper VLAN assignment.

Additional firewall configuration and rule checking took place throughout the month.

Despite troubleshooting taking longer than planned, the project remains on track for the November deadline.

## Identify and document variations

Variation 1: Extended time required for firewall troubleshooting.

Impact: Minor schedule compression for remaining configuration tasks.

Variation 2: Switch configuration changes to address incorrect APIPA addressing on DMZ PC.

Impact: slight delay in schedule or budget impact.

Variation 3: Additional unplanned task modifying Windows Server host file to access DMZ web server.

Impact: Resolved connectivity but added extra configuration work.

Monitor risks – update risk register

|  | Risk | Status | mitigation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Prolonged firewall misconfiguration | Improved but ongoing | Continuing testing |  |  |  |  |  |
|  | Incorrect addressing on DMZ PC | Resolved | Switch VLAN corrections applied |  |  |  |  |  |

Quality - Verify Prototype is meeting project technical requirements

- Criteria of project outputs

Functional DMZ website accessible from internal networks

Correct NAT and DNS behaviour across all zones

VLAN integrity

Firewall enforcing correct security policies

Stable addressing on all PCs and servers

Testing Procedures Used So Far

Multiple rounds of firewall testing covering:

NAT rule inspection

Security policy verification

Outbound internet tests

DNS resolution testing across internal hosts after configuration corrections.

Host based testing from Windows Server to DMZ website using host file update.

Connectivity testing from DMZ PC after correcting improper APIPA addressing.

Switch VLAN adjustments tested and verified.

Budget progress relative to projections

No new spending occurred in October.

Total remains: $12,860

Budget is still 100% on target.

Critical path analysis

Current Critical Path Sequence

Complete firewall troubleshooting (ongoing but major issues resolved) (done)

Finalise DNS and NAT across all devices (done)

Configure SIEM and Fleet Server (scheduled)

Integrate firewall logs with SIEM

Conduct full end-to-end testing

Remediate issues and finalise prototype

Prepare final documentation and presentation

# References: