# Monthly Project Report

# Team Members:

Adam, Liam, Mitchell Byrce

# Dated

30.9.25

## Procurement progress and tracking

All required hardware and software for the build phase has been acquired, including the Palo Alto Firewall, Cisco switches, all Cat5 cabling, Windows Server, Windows 10 client, Kali Linux VMs, and Ubuntu SIEM server.

Procurement is 100% complete, and no delays or sourcing issues were encountered.

All items have been verified as functional and ready for configuration.

## Project progress to timelines

Initial project scope completed on schedule.

Trello board and GitHub repository created in early September, meeting expected planning deadlines.

Cabling work completed ahead of schedule.

All virtual machines installed as planned; configuration tasks have commenced.

Base switch VLAN configuration completed on time.

Firewall configuration for internet access has experienced delays and is expected to be corrected by 07/10/2025.

Project is slightly behind timeline due to firewall issues but still recoverable.

## Identify and document variations

Variation 1: Additional troubleshooting time required for firewall NAT and outbound internet configuration.

Impact: Minor delay to network configuration tasks.

Variation 2: VM configuration changed, Windows Server and Palo Alto Firewall configured earlier to assist in baseline testing.

Impact: No effect on budget or timelines.

Variation 3: Extra testing sessions planned in early October to recover lost time.

Impact: Adjusted team workload but no schedule extension required.

Monitor risks – update risk register

|  | risk | status | Mitigation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Firewall misconfiguration delays | Active | Additional troubleshooting planned; NAT and security rules to be corrected by 07/10/25 |  |  |  |  |  |
|  | VM networking inconsistencies | Active | Rechecking adapter assignments and IP allocation early October |  |  |  |  |  |
|  | Configuration dependency delays (SIEM requires working firewall) | Active | Prioritising firewall fix before SIEM rollout |  |  |  |  |  |

Quality - Verify Prototype is meeting project technical requirements

Budget progress relative to projections

Project outputs must include a fully functional CSOC network prototype that meets:

Correct device interconnectivity

Working VLAN segmentation

Firewall rules with correct NAT and security policies

Functional Windows Server, SIEM, endpoints, and DMZ

Successful end-to-end testing results

Testing will verify system stability, security, and compliance with project requirements.

Testing done:

Project outputs must include a fully functional CSOC network prototype that meets:

Correct device interconnectivity

Working VLAN segmentation

Firewall rules with correct NAT and security policies

Functional Windows Server, SIEM, endpoints, and DMZ

Testing will verify system stability, security, and compliance with project requirements.

6. Budget Progress Relative to Projections

Total projected cost: $12,860

Actual expenditure: $12,860

No additional or unexpected costs.

Critical path analysis

Current Critical Path Sequence

Network Infrastructure Setup

Switch and Firewall Configuration (current delay)

VM Configuration and Baseline Testing

SIEM Deployment and Integration + DMZ

Firewall + SIEM Log Ingestion

End-to-End Testing

# References: